## Slide 1
Stakeholder | Role (Related to project) | Involvement | Impact | Power or Influence (H/M/L) | Interest (H/M/L) | Engagement
Director of Product | Project sponsor | They support the project, make high-level decisions, company’s influence, networking/relationships and sometimes act as a resource for them. | Positive: A success project could enhance their reputation and support their vision for the company. Negative: If the project fails, it could affect poorly on their decision-making and leadership. Resistance: Unlikely, given their role as project sponsor and interest in the project’s success. | H | M | I would have engage with them Manage Closely. I would have regular updates and consultation. Having regular meetings to discuss project progress, high-level decisions, and strategic alignment.
Landscape Designer/Web Designer | Project team member | They have design and technical expertise, internal networking, and software tools. | Positive: Opportunity for their professional growth and skills Negative: Changes in job responsibilities or focus, which may not align with their career goals or interests. Resistance: Possible, especially if they see the project as a threat to their current rule, or a shift in their responsibilities. | M | H | I would have engagement with them by Keeping Satisfied and Manage Closely. I would communicate with them frequently, ongoing communication, Involve them in key discussion related to design and web aspects of the project. Provide updates on how the project impacts their role and seek their input of their expertise.
Understanding stakeholders (stakeholder analysis)

## Slide 2
Stakeholder | Role (Related to project) | Involvement | Impact | Power or Influence (H/M/L) | Interest (H/M/L) | Engagement
Existing clients and their employees | Office Green customer | They provide feedback and insights of the product, and can have they participate in market testing. | Positive: Enhance service offerings and potential for improved workplace environment. Negative: They feel dissatisfied if new service doesn’t meet expectations. Resistance: Possible from clients who are less interested in Plant Pals. | M | L | Engagement with Showing Consideration. I would have semi-regular consultation, primarily to gather feedback. Update could be on monthly basis. Engage them through surveys or groups to understand their needs and preferences.
Office Green’s investors | Secondary stakeholder | They have financial support to your project, networking, and business expertise. | Positive: Increase revenue and company growth if the project succeeds. Negative: Financial loss and potential harm to the company’s reputation if the project failed. Resistance: Unlikely, as they are not involve in day-to-day operations and primarily concerned with the financial success of the company. | L | M | Engagement with Monitor. Communication would be rare I would share them with quarterly reports or updates. Communication is clear and focuses on project’s impact on company growth and financial health.
Understanding stakeholders (stakeholder analysis)

## Slide 3
Stakeholder | Role (Related to project) | Involvement | Impact | Power or Influence (H/M/L) | Interest (H/M/L) | Engagement
Office Green’s receptionist | Office Green employee | They can have customer interaction and feedback, internal communication about the service to the other employees and clients, and Office tools and system. | Positive: It could lead to an improved working environment and company reputation, Negative: Increased workload due to customer inquiries or confusion if not informed about the service. Resistance: Unlikely, but possible if they feel unprepared to handle customer queries. Or if it significantly increase their workload without support or training. | L | L | Engagement with Monitor. I would communicate with them primarily information updates closer to the project launch. Project training and resources to handle customer inquiries about Plant Pals. Updates might be monthly or as needed to prepare for post-launch activities.
Understanding stakeholders (stakeholder analysis)

## Slide 4
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
Power
high
low
med
high
low
Prioritizing stakeholders (power grid)
Director of Product
OG Investors
Clients & Employees
OG Receptionist
Drag each stakeholder’s box to the appropriate place on the power-interest grid
Interest
med
Landscape Designer/Web Designer