## WBS Spreadsheet
Milestone | Task ID | Task | Owner | Duration (days) | Notes
Establish a plant delivery and logistic plan | 1.1 | Source Materials for Packaging | Fulfillment Director | 10 days | Responsible for sourcing materials and ensuring they meet quality and sustainability standards
| 1.2 | Hire Delivery Drivers | Human Resources Specialist | 10 days | Manages hiring process, ensuring drivers are qualified and trained.
| 1.3 | Calculate Delivery Fees | Financial Analyst | 10 days | Develops pricing model considering distance, size, and delivery time.
Select and install supply chain management software and equipment | 2.1 | Supervise Vendor Setup for Inventory Management Software | Inventory Manager | 3 days | Coordinates with vendors for software installation, focusing on inventory management efficiency.
| 2.2 | Supervise Vendor Installation of Fulfillment Equipment | Fulfillment Director | 2 days | Oversees equipment installation, ensuring operational efficiency and safety.
| 2.3 | Determine Internal Safety Protocols for Equipment | Quality Assurance Tester | 10 days | Develops safety protocols and best practices for equipment use.
Develop and launch an employee training plan | 3.1 | Develop Training Sessions | Human Resources Specialist | 10 days | The Human Resources Specialist develops the training sessions with the help of the Training Manager
| 3.2 | Train Employees to Use Software and Equipment | Training Manager | 10 days | Conducts hands-on training sessions, ensuring employee competency.
| 3.3 | Monitor Progress and Improve Training Processes | Training Manager | 10 days | The Training Manager refines training processes