## Status Report
Project Name: Plant Pals Operations
Today's date: July 5
Summary |  |  |  | Overall Status (RAG)
We have installed new software to keep track of incoming orders and begun sending out the first test batch of Plant Pals to customers. However, we have run into issues with product quality, customer communication, and the delivery process. Our next milestones include sending the test batch customers newsletters on plant upkeep and sending out the second batch of plants. This report also includes top risks and issues that have arisen and how we intend to take action.
Completed Tasks and Milestones
Description | Date | Status | Owner |  | Comments
|  | Completed | IT Specialist
Began sending test batches of Plant Pals orders to customers | June 21 | Completed |  |  | The number of orders exceeded targets by 15%.
Upcoming Tasks and Milestones
Description | Date | Status | Owner |  | Comments
Send the first batch customers e-newsletters on how to take care of their plants. |  | Upcoming |  |  | The newsletter must follow Office Green’s brand design guidelines.
| July 19 | Upcoming | Fulfillment Director
Top Risks and Issues
Issue |  | Impact | Action |  |  | Owner
|  | Profit loss, complaints, and budget issues |  |  |  | Warehouse Operations Manager
The customer relations team is receiving only 30% of requests and complaints |  | Customer dissatisfaction | Fix problems with new customer service software
|  |  | Hire and train more delivery drivers |  |  | HR Specialist