## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | Positive Tablet Experience | Survey responses to question 3 | Highlight and build upon these positive aspects in marketing and future training
Customers | Went well | Waiter Instruction | Survey responses to question 4 | Reinforce and recognize the effective training of waitstaff in tablet usage
Customers | Went well | Ease of Use | Survey responses to question 5 | Continue to refine and maintain the user-friendly interface of the tablets
Customers | Needs improvement | Multiple Ordered Using Tablets | Survey responses to question 2 | Investigate barriers to multiple order placements and improve tablet functionality for this purpose
Customers | Needs improvement | Checkout Process | Survey responses to question 10 | Explore alternatives for cash payments and enhance the digital checkout process
Customers | Needs improvement | Technical Issues | Survey responses to question 15 | Implement a more robust technical support system and routine maintenance checks.
Project team | Went well | Tablet Installation and Functioning | Alex's and Gilly's feedback in the meeting | Continue the effective coordination with technical teams for installation in future rollouts.
Project team | Went well | Positive Updates in Kitchen Operations | Larissa's feedback in the meeting | Document these updates and consider applying them across other locations
Project team | Went well | Quick Resolution of Technical Issues | Seydou's feedback in the meeting | Update the process manual with these solutions for easy reference in the future
Project team | Needs improvement | Table Turn Time | Gilly's and Alex's feedback in the meeting | Analyze the current process and identify strategies to improve table turn time.
Project team | Needs improvement | Order Accuracy | Zane's and Larissa's feedback in the meeting | Review the tablet ordering system and staff training to enhance order accuracy.
Project team | Needs improvement | Waitstaff Training Process | Alex's feedback in the meeting | Develop an enhanced training program, possibly in multiple phases, to cover all aspects of service operations.