## Project Budget
Budget: Project Plant Pals Operations & Training
[7 empty] | TARGET BUDGET | ACTUAL/ FINAL SPEND | UNDER/ OVER
[7 empty] | 62000 | 0 | 62000
|  |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE DETAILS | HOURS | RATE | UNITS | $/UNIT
Milestone 1: Establish a plant delivery and logistics plan
Task 1: Purchase delivery trucks |  |  |  | 2 | 15000 |  | 30000 |  | -30000
Task 2: Source packaging materials |  |  |  | 1500 | 2 |  | 3000 |  | -3000
Task 3: Pay delivery drivers | Two delivery drivers | 160 | 15 |  |  |  | 2400 |  | -2400
-- | [5 empty] | Total | 35400 | 0
Milestone 2: Select and install supply chain management software and equipment
Task 1: Source Vendors | [5 empty] | 15000 | 15000 |  | -15000
-- | [5 empty] | Total | 15000 | 0
Milestone 3: Develop and launch an employee training program
Task 1: Develop training sessions | HR specialist | 80 | 50 |  |  |  | 4000 |  | -4000
Task 2: Train employees to use the software and equipment | Training Manager | 80 | 25 |  |  |  | 2000 |  | -2000
Task 3: Monitor employee progress and improve training processes | Training Manager | 80 | 25 |  |  |  | 2000 |  | -2000
-- | [5 empty] | Total | 8000 | 0
Reserve buffer | [6 empty] | 3600
TOTAL | [6 empty] | 62000 | 0